## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | utsav | 2026-10-11 | Java syntax validation is not implemented in the Code Submission Module. When Java code is submitted, the backend returns a message indicating that Java validation is not yet available. | Sprint 1 | utsav | Logical | Reviewed the existing validation logic and identified the need to integrate a Java-compatible parser or compiler into the Python backend. | 2026-10-11 | Closed | Issue has been resolved and also the user is able to see the in-detail insights of the pasted code in the editor.
2 | utsav | 2026-10-12 | The file-upload feature currently accepts Python .py files only. Java .java files cannot be uploaded and validated, although the project requires support for both Python and Java source files. | Sprint 1 | utsav | Logical | Reviewed the file-upload control and backend file-extension checks. Identified the changes required to support Java file uploads and language-specific syntax validation. | 2026-10-12 | closed | Java file upload and validation are pending. Retest the feature after implementing Java support.
3 | utsav | 2026-10-13 | The code submission module must handle empty or whitespace-only input and prevent it from being treated as a valid code submission. | Sprint 1 | utsav | User Interface | Added an empty-input check to the Python validation logic and reviewed the response returned for empty submissions. | 2026-10-13 | closed | Verify that empty and whitespace-only submissions return an appropriate error message.
4 | utsav | 2026-10-14 | The file-upload feature must reject unsupported file formats and display a clear message instead of attempting to validate them as Python or java source files. | Sprint 1 | utsav | Standards | Added or reviewed the file-extension check and the error message shown when an unsupported file is uploaded. | 2026-10-14 | closed | Test with a .txt file and confirm that the module rejects it with a clear message.
5 | utsav | 2026-10-15 | Syntax validation errors should be displayed clearly, including the error message and line number where available, so developers can identify the problem in their submitted code. | Sprint 1 | utsav | User Interface | Connected the backend validation response to the result area in the interface and displayed the syntax error message and line number when available. | 2026-10-15 | Closed | Test with incorrect Python code and confirm that the error message is readable and the reported line number is correct.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others